## Data
Nº de actividades: | 32 | [8 empty] | 9
Nº Simulaciones Monte Carlo | 20000 |  |  | RESETEAR | [5 empty] | 6
| Duración | [7 empty] | Coste | [42 empty] | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9
Actividad | Modelo | Cód. | µ | s | mín | "+prob" | máx | Slack | Cost_Var | Cost_Fijo | s | mín | "+prob" | máx | Cód. | Modelo |  | Precedentes | A0 | A1 | A2 | A3 | A4 | A5 | A6 | A7 | A8 | A9 | A10 | A11 | A12 | A13 | A14 | A15 | A16 | A17 | A18 | A19 | A20 | A21 | A22 | A23 | A24 | A25 | A26 | A27 | A28 | A29 | A30 | A31 | A32 | A33 | A34 | A35 | A36 | A37 | A38 | A39 | A40 | A41 | Af
A1 | Triangular | 4 | X | X | 10 | 15 | 20 | 0 | 1 | 0 | X | X | X | X | 1 | Determinista |  | A0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A2 | Triangular | 4 | X | X | 25 | 30 | 35 | 0 | 2.5 | 0 | X | X | X | X | 1 | Determinista |  | A1 | 1
A3 | Triangular | 4 | X | X | 20 | 30 | 40 | 0 | 4.5 | 0 | X | X | X | X | 1 | Determinista |  | A2 |  | 1
A4 | Triangular | 4 | X | X | 45 | 55 | 65 | 0 | 4.5 | 0 | X | X | X | X | 1 | Determinista |  | A3 |  | 1
A5 | Triangular | 4 | X | X | 60 | 70 | 80 | 0 | 7.5 | 0 | X | X | X | X | 1 | Determinista |  | A4 |  |  |  | 1 | bar: R1
A6 | Triangular | 4 | X | X | 80 | 90 | 100 | 0 | 3.5 | 0 | X | X | X | X | 1 | Determinista |  | A5 | bar: R1
A7 | Triangular | 4 | X | X | 50 | 70 | 90 | 0 | 10 | 0 | X | X | X | X | 1 | Determinista |  | A6 | bar: R1
A8 | Triangular | 4 | X | X | 20 | 25 | 30 | 0 | 0 | 650.5 | X | X | X | X | 1 | Determinista |  | A7 |  | 1
A9 | Triangular | 4 | X | X | 70 | 85 | 100 | 0 | 0 | 4200 | X | X | X | X | 1 | Determinista |  | A8 | [5 empty] | 1
A10 | Triangular | 4 | X | X | 70 | 85 | 100 | 0 | 0 | 3675 | X | X | X | X | 1 | Determinista |  | A9 | [5 empty] | 1
A11 | Triangular | 4 | X | X | 70 | 80 | 90 | 0 | 0 | 7000 | X | X | X | X | 1 | Determinista |  | A10 | bar: R2
A12 | Triangular | 4 | X | X | 100 | 110 | 120 | 0 | 0 | 75 | X | X | X | X | 1 | Determinista |  | A11 | [7 empty] | 1
A13 | Triangular | 4 | X | X | 70 | 80 | 90 | 0 | 14.4 | 500 | X | X | X | X | 1 | Determinista |  | A12 | [7 empty] | 1
A14 | Triangular | 4 | X | X | 25 | 30 | 35 | 0 | 6 | 100 | X | X | X | X | 1 | Determinista |  | A13 | [7 empty] | 1
A15 | Triangular | 4 | X | X | 12 | 15 | 18 | 0 | 6 | 0 | X | X | X | X | 1 | Determinista |  | A14 | [11 empty] | 1 |  | 1
A16 | Triangular | 4 | X | X | 170 | 190 | 210 | 0 | 1.8 | 300 | X | X | X | X | 1 | Determinista |  | A15 | [14 empty] | 1
A17 | Triangular | 4 | X | X | 45 | 55 | 65 | 0 | 4.8 | 300 | X | X | X | X | 1 | Determinista |  | A16 |  | 1
A18 | Triangular | 4 | X | X | 50 | 60 | 70 | 0 | 5.4 | 550 | X | X | X | X | 1 | Determinista |  | A17 | bar: R1
A19 | Triangular | 4 | X | X | 45 | 55 | 65 | 0 | 6 | 575 | X | X | X | X | 1 | Determinista |  | A18 | [17 empty] | 1
A20 | Triangular | 4 | X | X | 80 | 95 | 110 | 0 | 5.4 | 675 | X | X | X | X | 1 | Determinista |  | A19 |  |  |  | 1
A21 | Triangular | 4 | X | X | 20 | 25 | 30 | 0 | 3.6 | 275 | X | X | X | X | 1 | Determinista |  | A20 |  |  |  |  | 1 | [14 empty] | 1
A22 | Triangular | 4 | X | X | 18 | 20 | 22 | 0 | 3.6 | 275 | X | X | X | X | 1 | Determinista |  | A21 | [18 empty] | 1
A23 | Triangular | 4 | X | X | 35 | 40 | 45 | 0 | 4.8 | 287 | X | X | X | X | 1 | Determinista |  | A22 | [21 empty] | 1
A24 | Triangular | 4 | X | X | 30 | 40 | 50 | 0 | 3 | 275 | X | X | X | X | 1 | Determinista |  | A23 | [18 empty] | 1
A25 | Triangular | 4 | X | X | 35 | 45 | 55 | 0 | 8 | 75 | X | X | X | X | 1 | Determinista |  | A24 | [21 empty] | 1
A26 | Triangular | 4 | X | X | 75 | 85 | 95 | 0 | 9.6 | 125 | X | X | X | X | 1 | Determinista |  | A25 | [8 empty] | 1
A27 | Triangular | 4 | X | X | 75 | 80 | 85 | 0 | 8 | 100 | X | X | X | X | 1 | Determinista |  | A26 | [21 empty] | 1 |  |  |  | 1
A28 | Triangular | 4 | X | X | 45 | 60 | 75 | 0 | 25 | 375 | X | X | X | X | 1 | Determinista |  | A27 | [22 empty] | 1 | bar: R3; R8 to R9
A29 | Triangular | 4 | X | X | 12 | 15 | 18 | 0 | 2 | 0 | X | X | X | X | 1 | Determinista |  | A28 | [10 empty] | 1 | [13 empty] | 1
A30 | Triangular | 4 | X | X | 50 | 60 | 70 | 0 | 7 | 75 | X | X | X | X | 1 | Determinista |  | A29 | bar: R4; R9
A31 | Triangular | 4 | X | X | 12 | 15 | 18 | 0 | 3 | 0 | X | X | X | X | 1 | Determinista |  | A30 | [15 empty] | 1 | 1 | [12 empty] | 1
A32 | Triangular | 4 | X | X | 12 | 15 | 18 | 0 | 3 | 0 | X | X | X | X | 1 | Determinista |  | A31 | bar: R6 to R7
[18 empty] | A32 | [27 empty] | 1 |  |  |  | 1 | bar: R5
Actividad | Modelo | Cód. | µ | s | mín | "+prob" | máx | P / I | t / C | Riesgo/Act | [6 empty] | R1 | A33 |  |  | 1
A33 | Uniforme | 2 | X | X | 0 | X | 0.03 | P | t | R1 | [6 empty] | R2 | A34 | [6 empty] | 1
A33 | Uniforme | 2 | X | X | 5 | X | 20 | I | 2.5 | 2 | [6 empty] | R3 | A35 | [9 empty] | 1
A34 | Uniforme | 2 | X | X | 0.3 | X | 0.5 | P | t | R2 | [6 empty] | R4 | A36 | [12 empty] | 1
A34 | Uniforme | 2 | X | X | 20 | X | 50 | I | 3.5 | 6 | [6 empty] | R5 | A37 | [28 empty] | 1
A35 | Uniforme | 2 | X | X | 0.03 | X | 0.1 | P | t | R3 | [6 empty] | R6 | A38 | [26 empty] | 1
A35 | Uniforme | 2 | X | X | 50 | X | 75 | I | 0 | 9 | [6 empty] | R7 | A39 | [30 empty] | 1
A36 | Uniforme | 2 | X | X | 0.1 | X | 0.3 | P | t | R4 | [6 empty] | R8 | A40 | [23 empty] | 1
A36 | Uniforme | 2 | X | X | 5 | X | 20 | I | 0 | 12 | [6 empty] | R9 | A41 | [20 empty] | 1
A37 | Uniforme | 2 | X | X | 0.1 | X | 0.3 | P | t | R5 | [7 empty] | Af | [32 empty] | 1
A37 | Uniforme | 2 | X | X | 20 | X | 50 | I | 25 | 28
A38 | Uniforme | 2 | X | X | 0.03 | X | 0.1 | P | t | R6
A38 | Uniforme | 2 | X | X | 5 | X | 20 | I | 9.6 | 26
A39 | Uniforme | 2 | X | X | 0 | X | 0.03 | P | t | R7
A39 | Uniforme | 2 | X | X | 20 | X | 50 | I | 7 | 30
A40 | Uniforme | 2 | X | X | 0.1 | X | 0.3 | P | t | R8
A40 | Uniforme | 2 | X | X | 20 | X | 50 | I | 4.8 | 23
A41 | Uniforme | 2 | X | X | 0.03 | X | 0.1 | P | t | R9
A41 | Uniforme | 2 | X | X | 5 | X | 20 | I | 5.4 | 20
R. Coste1 | Uniforme | 2 | X | X | 0.3 | X | 0.5 | P | C | R10
R. Coste1 | Uniforme | 2 | X | X | 100 | X | 750 | I | C | 2
R. Coste2 | Uniforme | 2 | X | X | 0.03 | X | 0.1 | P | C | R11
R. Coste2 | Uniforme | 2 | X | X | 750 | X | 2500 | I | C | 8
R. Coste3 | Uniforme | 2 | X | X | 0.03 | X | 0.1 | P | C | R12
R. Coste3 | Uniforme | 2 | X | X | 100 | X | 750 | I | C | 13
R. Coste4 | Uniforme | 2 | X | X | 0.03 | X | 0.1 | P | C | R13
R. Coste4 | Uniforme | 2 | X | X | 750 | X | 2500 | I | C | 26
R. Coste5 | Uniforme | 2 | X | X | 0 | X | 0.03 | P | C | R14
R. Coste5 | Uniforme | 2 | X | X | 0 | X | 100 | I | C | 30
R. Coste6 | Uniforme | 2 | X | X | 0.03 | X | 0.1 | P | C | R15
R. Coste6 | Uniforme | 2 | X | X | 2500 | X | 6000 | I | C | 31
En la celda sombreada de color ROJO se debe poner la DURACIÓN VARIABLE correspondiente a la actividad que afecta ese riesgo de duración
En cada celda sombreada de color AZUL se debe poner el Número de la ACTIVIDAD correspondiente afectada por este riesgo de Duración y/o Coste
Generar Actividades
Generar Riesgos Duracion
Generar Riesgos Coste

## Risk Id
R_Cost | R_Dur | RISK LIST
|  | RISK | Phase | PROBABILITY | COST IMPACT |  | TIME IMPACT |  | ACTIVITY AFFECTED | EXPLANATION
| R1 | Technical complexity of the engineering project | Engineering | VL | - |  | B | 5-20 | 6 | Technical complexity in the engineering phase. Complexity in the drafting of the technical project. Complexity due to the novelty of the project to be executed.
RC_1 | R2 | Change of requirements in the project | Engineering | H | L | 100-750 | M | 20-50 | 2 | Changes proposed by the promoter
RC_2 |  | Inadequate supplier management | Procurement | L | M | 750-2500 | - |  | 8
RC_3 | R3 | Supply chain disruptions | Procurement | L | L | 100-750 | A | 50-75 | 13 | Microchips; Suez Canal
| R4 | Inaccurate internal needs analysis | Procurement | M | - |  | B | 5-20 | 12
| R5 | Health and safety hazards | Construction | M | - |  | M | 20-50 | 20
RC_4 | R6 | Adverse weather conditions | Construction | L | M | 750-2500 | B | 5-20 | 26 | Waste (asbestos), seepage, soil type problems, …
RC_5 | R7 | Difficulties in obtaining permits and licences | Construction | VL | VL | 0-100 | M | 20-50 | 30
| R8 | Availability of skilled labour | Construction | M | - |  | M | 20-50 | 28
| R9 | Availability of construction materials on time | Construction | L | - | - | M | 20-50 | 23
RC_6 |  | Changes in the price of raw materials | Construction | L | H | 2500-6000 | - |  | 31
PROBABILITY
|  |  | LEVEL | INTERVAL (%)
|  |  | VERY LOW (VL) | 0-3
|  |  | LOW (L) | 3-10
|  |  | MEDIUM (M) | 10-30
|  |  | HIGH (H) | 30-50
|  |  | VERY HIGH (VH) | 50-100
COST IMPACT
|  |  | LEVEL | INTERVAL (%)
|  |  | VERY LOW (VL) | 0-100
|  |  | LOW (L) | 100-750
|  |  | MEDIUM (M) | 750-2500
|  |  | HIGH (H) | 2500-6000
|  |  | VERY HIGH (VH) | >6000
TIME IMPACT
|  |  | LEVEL | INTERVAL (%)
|  |  | VERY LOW (VL) | 0-5
|  |  | LOW (L) | 5-20
|  |  | MEDIUM (M) | 20-50
|  |  | HIGH (H) | 50-75
|  |  | VERY HIGH (VH) | >75

## Prioritization
Risk Prioritization
|  |  | P | I | PxI | Risk Rating | Prioritisation |  |  | Activity | Ranking_Dur | Ranking_Cost
| R1 | 1_d | MB | B | 0.01 | Medium | 9 | 14 | R1 | 2 | 9 | 13
| R2 | 2_d | A | M | 0.14 | Low | 1 | 1 | R2 | 6 | 3 | 7
| R3 | 3_d | B | A | 0.12 | Low | 2 | 2 | R3 | 9 | 1 | 14
| R4 | 4_d | M | B | 0.05 | Medium | 6 | 10 | R4 | 12 | 5 | 14
| R5 | 5_d | M | M | 0.1 | Low | 3 | 4 | R5 | 28 | 2 | 4
| R6 | 6_d | B | B | 0.03 | Low | 7 | 11 | R6 | 26 | 8 | 9
| R7 | 7_d | MB | M | 0.02 | Low | 8 | 13 | R7 | 30 | 6 | 10
| R8 | 8_d | M | M | 0.1 | Medium | 3 | 4 | R8 | 23 | 4 | 8
| R9 | 9_d | B | M | 0.06 | Low | 5 | 7 | R9 | 20 | 7 | 11
R2 | RC1 | 2_c | A | B | 0.07 | Low | 2 | 6 | R10 | 6 | 10 | 5
| RC2 | 3_c | B | M | 0.06 | Low | 3 | 7 | R11 | 8 | 10 | 2
R3 | RC3 | 4_c | B | B | 0.03 | Low | 5 | 11 | R12 | 9 | 10 | 6
R6 | RC4 | 7_c | B | M | 0.06 | Low | 3 | 7 | R13 | 26 | 10 | 3
R7 | RC5 | 8_c | MB | MB | 0.005 | Low | 6 | 15 | R14 | 30 | 10 | 12
| RC6 | 10_c | B | A | 0.12 | Medium | 1 | 2 | R15 | 31 | 10 | 1

## Risk Matrix
Probability | %
Very High (VH) | 50-100 | 0.9 | 0.045 | 0.09 | 0.18 | 0.36 | 0.72
High (H) | 30-50 | 0.7 | 0.035 | 0.07 | 0.14 | 0.28 | 0.56
Medium (M) | 10-30 | 0.5 | 0.025 | 0.05 | 0.1 | 0.2 | 0.4
Low (L) | 3-10 | 0.3 | 0.015 | 0.03 | 0.06 | 0.12 | 0.24
Very Low (VL) | 0-3 | 0.1 | 0.005 | 0.01 | 0.02 | 0.04 | 0.08
|  |  | 0.05 | 0.1 | 0.2 | 0.4 | 0.8
|  |  | 0-5 | 5-20 | 20-50 | 50-75 | >75
Impact Duration (days) |  |  | Very Low (VL) | Low (L) | Medium (M) | High (H) | Very High (VH)
|  |  | 0-100 | 100-750 | 750-2500 | 2500-6000 | > 6000
Impact Cost (x1000 monetary units) |  |  | Very Low (VL) | Low (L) | Medium (M) | High (H) | Very High (VH)

## Dur_Cost_Percentil
Percentile | Duration | Cost
95 | 323.4339 | 30339.316

## Risk ranking
Row | Duration_with_Ri | Cost_with_Ri | Difference_Duration_with_Ri | Ranking_Dur | Difference_Cost_with_Ri | Ranking_Cost
R1 | 323.7688 | 30339.5517 | 0.33481 | 9 | 0.2357 | 13
R2 | 346.073 | 30407.6755 | 22.639 | 3 | 68.3595 | 7
R3 | 349.7641 | 30339.316 | 26.3302 | 1 | 0 | 14
R4 | 325.4894 | 30339.316 | 2.0554 | 5 | 0 | 14
R5 | 346.0996 | 31089.6776 | 22.6657 | 2 | 750.3616 | 4
R6 | 324.1948 | 30352.4762 | 0.76083 | 8 | 13.1602 | 9
R7 | 324.4501 | 30349.0131 | 1.0162 | 6 | 9.6971 | 10
R8 | 338.2516 | 30396.0422 | 14.8177 | 4 | 56.7262 | 8
R9 | 324.2968 | 30345.5673 | 0.86284 | 7 | 6.2513 | 11
R10 | 323.4339 | 30752.8693 | 0 | 10 | 413.5533 | 5
R11 | 323.4339 | 31105.8537 | 0 | 10 | 766.5377 | 3
R12 | 323.4339 | 30420.7213 | 0 | 10 | 81.4053 | 6
R13 | 323.4339 | 31116.6659 | 0 | 10 | 777.3499 | 2
R14 | 323.4339 | 30340.0413 | 0 | 10 | 0.72532 | 12
R15 | 323.4339 | 33400.2433 | 0 | 10 | 3060.9273 | 1