## Activities
Activity_ID | Activity_Number | Phase | Predecessors | Schedule_Risk_IDs | Cost_Risk_IDs | All_Connected_Risk_IDs | Connected_Risk_Names | Duration_Distribution | Duration_Min_Days | Duration_Most_Likely_Days | Duration_Max_Days | Lag | Cost_Distribution | Cost_Min_x1000 | Cost_Most_Likely_x1000 | Cost_Max_x1000 | Variable_Cost_Distribution | Variable_Cost_Min_x1000 | Variable_Cost_per_x1000 | Variable_Cost_Max_Days_x1000 | Source_Excel_Row
A1 | 1 | Engineering | Ai |  |  |  |  | Binomial | 10 | 15 | 20 | 0 | PERT | 0 | 0 | 0 | PERT | 0.75 | 1 | 1.25 | 8
A2 | 2 | Engineering | A1 | R2 | R10 | R2, R10 | R2: Change of requirements in the project; R10: Change of requirements in the project | Binomial | 25 | 30 | 35 | 0 | PERT | 0 | 0 | 0 | PERT | 1.875 | 2.5 | 3.125 | 9
A3 | 3 | Engineering | A1 |  |  |  |  | Binomial | 20 | 30 | 40 | 0 | PERT | 0 | 0 | 0 | PERT | 3.375 | 4.5 | 5.625 | 10
A4 | 4 | Engineering | A2, A3 |  |  |  |  | Binomial | 45 | 55 | 65 | 0 | PERT | 0 | 0 | 0 | PERT | 3.375 | 4.5 | 5.625 | 11
A5 | 5 | Engineering | A2 |  |  |  |  | Binomial | 60 | 70 | 80 | 0 | PERT | 0 | 0 | 0 | PERT | 5.625 | 7.5 | 9.375 | 12
A6 | 6 | Engineering | A2 | R1 |  | R1 | R1: Technical complexity of the engineering project | Binomial | 80 | 90 | 100 | 0 | PERT | 0 | 0 | 0 | PERT | 2.625 | 3.5 | 4.375 | 13
A7 | 7 | Engineering | A1 |  |  |  |  | Binomial | 50 | 70 | 90 | 0 | PERT | 0 | 0 | 0 | PERT | 7.5 | 10 | 12.5 | 14
A8 | 8 | Procurement | A5 |  | R11 | R11 | R11: Inadequate supplier management | Binomial | 20 | 25 | 30 | 0 | PERT | 487.875 | 650.5 | 813.125 | PERT | 0 | 0 | 0 | 15
A9 | 9 | Procurement | A5 |  |  |  |  | Binomial | 70 | 85 | 100 | 0 | PERT | 3150 | 4200 | 5250 | PERT | 0 | 0 | 0 | 16
A10 | 10 | Procurement | A6 |  |  |  |  | Binomial | 70 | 85 | 100 | 0 | PERT | 2756.25 | 3675 | 4593.75 | PERT | 0 | 0 | 0 | 17
A11 | 11 | Procurement | A7 |  |  |  |  | Binomial | 70 | 80 | 90 | 0 | PERT | 5250 | 7000 | 8750 | PERT | 0 | 0 | 0 | 18
A12 | 12 | Procurement | A7 | R4 |  | R4 | R4: Inaccurate internal needs analysis | Binomial | 100 | 110 | 120 | 0 | PERT | 56.25 | 75 | 93.75 | PERT | 0 | 0 | 0 | 19
A13 | 13 | Procurement | A7 | R3 | R12 | R3, R12 | R3: Supply chain disruptions; R12: Supply chain disruptions | Binomial | 70 | 80 | 90 | 0 | PERT | 375 | 500 | 625 | PERT | 10.8 | 14.4 | 18 | 20
A14 | 14 | Procurement | A11, A13 |  |  |  |  | Binomial | 25 | 30 | 35 | 0 | PERT | 75 | 100 | 125 | PERT | 4.5 | 6 | 7.5 | 21
A15 | 15 | Procurement | A14 |  |  |  |  | Binomial | 12 | 15 | 18 | 0 | PERT | 0 | 0 | 0 | PERT | 4.5 | 6 | 7.5 | 22
A16 | 16 | Procurement | A1 |  |  |  |  | Binomial | 170 | 190 | 210 | 0 | PERT | 225 | 300 | 375 | PERT | 1.35 | 1.8 | 2.25 | 23
A17 | 17 | Construction | A2 |  |  |  |  | Binomial | 45 | 55 | 65 | 0 | PERT | 225 | 300 | 375 | PERT | 3.6 | 4.8 | 6 | 24
A18 | 18 | Construction | A17 |  |  |  |  | Binomial | 50 | 60 | 70 | 0 | PERT | 412.5 | 550 | 687.5 | PERT | 4.05 | 5.4 | 6.75 | 25
A19 | 19 | Construction | A3 |  |  |  |  | Binomial | 45 | 55 | 65 | 0 | PERT | 431.25 | 575 | 718.75 | PERT | 4.5 | 6 | 7.5 | 26
A20 | 20 | Construction | A3, A4 | R5 |  | R5 | R5: Health and safety hazards | Binomial | 80 | 95 | 110 | 0 | PERT | 506.25 | 675 | 843.75 | PERT | 4.05 | 5.4 | 6.75 | 27
A21 | 21 | Construction | A18 |  |  |  |  | Binomial | 20 | 25 | 30 | 0 | PERT | 206.25 | 275 | 343.75 | PERT | 2.7 | 3.6 | 4.5 | 28
A22 | 22 | Construction | A21 |  |  |  |  | Binomial | 18 | 20 | 22 | 0 | PERT | 206.25 | 275 | 343.75 | PERT | 2.7 | 3.6 | 4.5 | 29
A23 | 23 | Construction | A18 | R9 |  | R9 | R9: Availability of construction materials on time | Binomial | 35 | 40 | 45 | 0 | PERT | 215.25 | 287 | 358.75 | PERT | 3.6 | 4.8 | 6 | 30
A24 | 24 | Construction | A21 |  |  |  |  | Binomial | 30 | 40 | 50 | 0 | PERT | 206.25 | 275 | 343.75 | PERT | 2.25 | 3 | 3.75 | 31
A25 | 25 | Construction | A8 |  |  |  |  | Binomial | 35 | 45 | 55 | 0 | PERT | 56.25 | 75 | 93.75 | PERT | 6 | 8 | 10 | 32
A26 | 26 | Construction | A21, A25 | R6 | R13 | R6, R13 | R6: Adverse weather conditions; R13: Adverse weather conditions | Binomial | 75 | 85 | 95 | 0 | PERT | 93.75 | 125 | 156.25 | PERT | 7.2 | 9.6 | 12 | 33
A27 | 27 | Construction | A9, A22, A23 |  |  |  |  | Binomial | 75 | 80 | 85 | 0 | PERT | 75 | 100 | 125 | PERT | 6 | 8 | 10 | 34
A28 | 28 | Construction | A10, A24 | R8 |  | R8 | R8: Availability of skilled labour | Binomial | 45 | 60 | 75 | 0 | PERT | 281.25 | 375 | 468.75 | PERT | 18.75 | 25 | 31.25 | 35
A29 | 29 | Construction | A12, A20 |  |  |  |  | Binomial | 12 | 15 | 18 | 0 | PERT | 0 | 0 | 0 | PERT | 1.5 | 2 | 2.5 | 36
A30 | 30 | Construction | A15, A16, A29 | R7 | R14 | R7, R14 | R7: Difficulties in obtaining permits and licences; R14: Difficulties in obtaining permits and licences | Binomial | 50 | 60 | 70 | 0 | PERT | 56.25 | 75 | 93.75 | PERT | 5.25 | 7 | 8.75 | 37
A31 | 31 | Construction | A26, A30 |  | R15 | R15 | R15: Changes in the price of raw materials | Binomial | 12 | 15 | 18 | 0 | PERT | 0 | 0 | 0 | PERT | 2.25 | 3 | 3.75 | 38
A32 | 32 | Construction | A27, A28, A31 |  |  |  |  | Binomial | 12 | 15 | 18 | 0 | PERT | 0 | 0 | 0 | PERT | 2.25 | 3 | 3.75 | 39

## Risks
Risk_ID | Risk_Type | Source_Risk_Name | Phase | Affected_Activity_ID | Affected_Activity_Number | Probability_Level | Probability_Level_Interval | Probability_Distribution | Probability_Model_Code | Probability_Min | Probability_Max | Severity_Level | Severity_Level_Note | Severity_Interval_Published | Severity_Min_Published | Severity_Max_Published | Impact_Distribution | Impact_Model_Code | Impact_Min | Impact_Max | Impact_Units | Raw_Data_Activity_Value | Raw_Target_Type | Explanation | Source_Cost_Risk_Code_Raw | Source_Schedule_Risk_Code_Raw | Probability_Source_Row_Index | Impact_Source_Row_Index
R1 | Schedule | Technical complexity of the engineering project | Engineering | A6 | 6 | VL | 0-0.03 | Uniform | 2 | 0 | 0.03 | B | Bajo / Low in original Spanish scale | 5-20 | 5 | 20 | DiscreteUniform | 2 | 5 | 20 | days | 2 | t | Technical complexity in the engineering phase. Complexity in the drafting of the technical project. Complexity due to the novelty of the project to be executed. |  | R1 | 42 | 43
R2 | Schedule | Change of requirements in the project | Engineering | A2 | 2 | H | 0.30-0.50 | Uniform | 2 | 0.3 | 0.5 | M | Medium | 20-50 | 20 | 50 | DiscreteUniform | 2 | 20 | 50 | days | 6 | t | Changes proposed by the promoter |  | R2 | 44 | 45
R3 | Schedule | Supply chain disruptions | Procurement | A13 | 13 | L | 0.03-0.10 | Uniform | 2 | 0.03 | 0.1 | A | Alto / High in original Spanish scale | 50-75 | 50 | 75 | DiscreteUniform | 2 | 50 | 75 | days | 9 | t | Microchips; Suez Canal |  | R3 | 46 | 47
R4 | Schedule | Inaccurate internal needs analysis | Procurement | A12 | 12 | M | 0.10-0.30 | Uniform | 2 | 0.1 | 0.3 | B | Bajo / Low in original Spanish scale | 5-20 | 5 | 20 | DiscreteUniform | 2 | 5 | 20 | days | 12 | t |  |  | R4 | 48 | 49
R5 | Schedule | Health and safety hazards | Construction | A20 | 20 | M | 0.10-0.30 | Uniform | 2 | 0.1 | 0.3 | M | Medium | 20-50 | 20 | 50 | DiscreteUniform | 2 | 20 | 50 | days | 28 | t |  |  | R5 | 50 | 51
R6 | Schedule | Adverse weather conditions | Construction | A26 | 26 | L | 0.03-0.10 | Uniform | 2 | 0.03 | 0.1 | B | Bajo / Low in original Spanish scale | 5-20 | 5 | 20 | DiscreteUniform | 2 | 5 | 20 | days | 26 | t | Waste (asbestos), seepage, soil type problems, … |  | R6 | 52 | 53
R7 | Schedule | Difficulties in obtaining permits and licences | Construction | A30 | 30 | VL | 0-0.03 | Uniform | 2 | 0 | 0.03 | M | Medium | 20-50 | 20 | 50 | DiscreteUniform | 2 | 20 | 50 | days | 30 | t |  |  | R7 | 54 | 55
R8 | Schedule | Availability of skilled labour | Construction | A28 | 28 | M | 0.10-0.30 | Uniform | 2 | 0.1 | 0.3 | M | Medium | 20-50 | 20 | 50 | DiscreteUniform | 2 | 20 | 50 | days | 23 | t |  |  | R8 | 56 | 57
R9 | Schedule | Availability of construction materials on time | Construction | A23 | 23 | L | 0.03-0.10 | Uniform | 2 | 0.03 | 0.1 | M | Medium | 20-50 | 20 | 50 | DiscreteUniform | 2 | 5 | 20 | days | 20 | t |  |  | R9 | 58 | 59
R10 | Cost | Change of requirements in the project | Engineering | A2 | 2 | H | 0.30-0.50 | Uniform | 2 | 0.3 | 0.5 | L | Low | 100-750 | 100 | 750 | Uniform | 2 | 100 | 750 | x1000 monetary units | 2 | C | Changes proposed by the promoter | RC_1 | R2 | 60 | 61
R11 | Cost | Inadequate supplier management | Procurement | A8 | 8 | L | 0.03-0.10 | Uniform | 2 | 0.03 | 0.1 | M | Medium | 750-2500 | 750 | 2500 | Uniform | 2 | 750 | 2500 | x1000 monetary units | 8 | C |  | RC_2 |  | 62 | 63
R12 | Cost | Supply chain disruptions | Procurement | A13 | 13 | L | 0.03-0.10 | Uniform | 2 | 0.03 | 0.1 | L | Low | 100-750 | 100 | 750 | Uniform | 2 | 100 | 750 | x1000 monetary units | 13 | C | Microchips; Suez Canal | RC_3 | R3 | 64 | 65
R13 | Cost | Adverse weather conditions | Construction | A26 | 26 | L | 0.03-0.10 | Uniform | 2 | 0.03 | 0.1 | M | Medium | 750-2500 | 750 | 2500 | Uniform | 2 | 750 | 2500 | x1000 monetary units | 26 | C | Waste (asbestos), seepage, soil type problems, … | RC_4 | R6 | 66 | 67
R14 | Cost | Difficulties in obtaining permits and licences | Construction | A30 | 30 | VL | 0-0.03 | Uniform | 2 | 0 | 0.03 | VL | Very low | 0-100 | 0 | 100 | Uniform | 2 | 0 | 100 | x1000 monetary units | 30 | C |  | RC_5 | R7 | 68 | 69
R15 | Cost | Changes in the price of raw materials | Construction | A31 | 31 | L | 0.03-0.10 | Uniform | 2 | 0.03 | 0.1 | H | High | 2500-6000 | 2500 | 6000 | Uniform | 2 | 2500 | 6000 | x1000 monetary units | 31 | C |  | RC_6 |  | 70 | 71